## Development of religious places
Gamperaliya - Rapid Rural Development Programme - 2019 | [22 empty] | Annex D
Physical and Financial Progress of the Month of 31 March 2019
Kaluthara District
Palindanuwara Divisional Secretariate
No. | Name of the Project | Electorate | D.S. Division | G.N. Division | Sector | Length(k.m.m)/ Area (sq Mn.) | Approvd Amount (Rs) | Implementing Agency | Name of the Contractor/ Society | Progress | [11 empty] | No.of Benifisharies | Remarks
[10 empty] | Financial |  | Physical
[11 empty] | % | A | B
[13 empty] | B1 | B2 | B3 | B4 | C | D | E | F | G
1 | Ilukpatha Kovila. | Agalwattha | Palindanuwara | 835 A Elukpatha | RC |  | 500000 | Divi. Sec. | Ilukpatha Marimutthu Amman Kovila. Dayaka Sabawa | [6 empty] | √ | [5 empty] | 120
2 | Mohmadiya watta Lower Diviton Kovila. | Do | Do | 835 B Lathpadura East | RC |  | 500000 | Do |  |  |  | √ | [9 empty] | 500
3 | Citta gawesi Medation center | Do | Do |  | RC |  | 500000 | Do | Eleders Socity Lathpadura East | 485000 | 100 | [9 empty] | √ | 350
4 | Delkitwatta Main Kovila. | Do | Do |  | RC |  | 500000 | Do | Delkit Mutthumari Amman Kovila. Dayaka Sabawa | [6 empty] | √ | [5 empty] | 95
5 | Maraghadeniya Mahindaramaya Temple | Do | Do | 835 C Maragadeniya | RC |  | 500000 | Do | Temple Dayaka Sabawa | [6 empty] | √ | [5 empty] | 500
6 | Pelanda Rajamha wihara Temple | Do | Do | 836 Pelenda | RC |  | 500000 | Do | Eleders Socity 836 Pelanda | [7 empty] | √ |  |  |  |  | 452
7 | Pelanda Mosque | Do | Do |  | RC |  | 500000 | Do | Eleders Socity 836 Pelanda | [9 empty] | √ |  |  | 235
8 | Gangarama Temple | Do | Do | 836 D Athweltota | RC |  | 500000 | Do |  |  |  | √ | [9 empty] | 200
9 | Asweliya Marimutthu Amman Kovila. | Do | Do | 836 F Galahitiya | RC |  | 500000 | Do | Asweliya Mutthumari Amman Kovila. . Dayaka Sabawa | [6 empty] | √ | [5 empty] | 45
10 | Makeli Temple | Do | Do | 836 L Kosgulana | RC |  | 500000 | Do |  |  |  |  | √ | [8 empty] | 287
11 | Sri Wipulasiri Temple | Do | Do | 838 Hedigalla | RC |  | 500000 | Do |  |  |  |  | √ | [8 empty] | 275
12 | Magura Sri Gangarama Ancient Temple | Do | Do | 839 D Magura Est. | RC |  | 500000 | Do | Temple Dayaka Sabawa | [6 empty] | √ | [5 empty] | 238
13 | Gurulubedda Rathnapalaramaya | Do | Do | 840 A Panigala | RC |  | 500000 | Do |  |  |  |  | √ | [8 empty] | 280
14 | Galtundola Temple | Do | Do | 841 A Igurudaluwa | RC |  | 500000 | Do | Temple Dayaka Sabawa | [8 empty] | √ |  |  |  | 412
15 | Igrudaluwa Temple | Do | Do |  | RC |  | 500000 | Do | Temple Dayaka Sabawa | [6 empty] | √ | [5 empty] | 750
16 | Morapitiya Mahindarama Temple | Do | Do | 836 H Morapitiya | RC |  | 500000 | Do | Temple Dayaka Sabawa | [6 empty] | √ | [5 empty] | 492
| Total | [5 empty] | 8000000 |  |  | 485000 | [11 empty] | 5231