## ජල යෝජනා
Gamperaliya - Rapid Rural Development Programme - 2019
Physical and Financial Progress of the Month of 31 May 2019
Kaluthara District
Palindanuwara Divisional Secretariate | [21 empty] | Annex D
No. | Name of the Project | Electorate | D.S. Division | G.N. Division | Sector | Length(k.m.m)/ Area (sq Mn.) | Approvd Amount (Rs) | Implementing Agency | Name of the Contractor/ Society | Progress | [11 empty] | No.of Benifisharies | Remarks
[10 empty] | Financial |  | Physical
[11 empty] | % | A | B
[13 empty] | B1 | B2 | B3 | B4 | C | D | E | F | G
1 | Galahitiya New Vileag Water Supply Project | Agalwattha | Palindanuwara | 836 F Galhitiya | WS |  | 1000000 | Divi. Sec. | Eleders Socity Galhitya. | [11 empty] | √ | 58
2 | Ransirigama Water Supply Project | Do | Do | 836 E Palanda West | WS |  | 1000000 | Do | Eleders Socity Pelandha W. | [11 empty] | √ | 150
3 | Pelanda Wattha Water Supply Project | Do | Do | 836 E Palanda West | WS |  | 1000000 | Do | Eleders Socity Pelandha W. | [11 empty] | √ | 60
4 | Diaganna Water Supply Project | Do | Do | 836 N Diganna | WS |  | 1000000 | Do | Diganna Rural Divlopment Socity | 970857.37 | [10 empty] | √ | 35
5 | Diganna Alamodara Water Supply Project | Do | Do | 837 N Diganna | WS |  | 1000000 | Do | Diganna Rural Divlopment Socity | 969950 | [10 empty] | √ | 40
6 | Diaganna Water Supply Project part 2 | Do | Do | 838 N Diganna |  |  | 500000 | Do | Diganna Rural Divlopment Socity | [9 empty] | √ |  |  | 35
| Total |  |  |  |  | 0 | 5500000 |  |  | 1940807.37 | [11 empty] | 343
14153788.75

## Sheet1
ජල | 5500000
නිවාස | 16500000
මාර්ග | 39000000
ක්‍රිඩාපිටි | 1000000
ආගමික | 8000000
70000000