## මාර්ග
| Gamperaliya- Rapid Rural Development Programme - 2019 | [16 empty] | Annexure D
Physical and Financial Progress of the Month of Month of 31 May 2019 ( 2019.05.31 )
District : Kalutara - DS Division -Palindanuwaara
project No | No | Name of the Project | Electorate | DS Division | GN Division | Sector | Length(k.m/m.)/ Area (/sq.m.) | Approved Amount (Rs, Mn.) | Implementing Agency | Name of the Contractor/ Society | Progress | [11 empty] | No. of Beneficiaries | Remarks
[11 empty] | Financial |  | Physical **
[11 empty] | Expenditure (Rs. Mn.) | % | A | B |  |  |  | C | D | E | F | G
[14 empty] | B1 | B2 | B3 | B4
36100 023 | 1 | Development of Panadadukanda road - near the Mr. Shantha's House |  |  | 834 Bellana | RA | 215 | 0.5 | Divisional Secretarite | Eaksath Govi So. |  |  |  | √ | [8 empty] | 60
36085 024 | 2 | Concreting of the Bellana watta road |  |  | 834 A Bellana East | RA | 195 | 0.5 |  | Haldola Govi So. |  |  |  | √ | [8 empty] | 456
36095 025 | 3 | Development of Ganagala Road- go to Ms. Premalatha' s House |  |  | 834 B Kapugama | RA | 192 | 0.5 |  | Samagi elder-Society | [8 empty] | √ |  |  |  | 97
36090 026- A | 4 | Development of the Diyannagoda(near the UNP office) road |  |  | 834 C Viharagama | RA | 150 | 0.5 | [5 empty] | √ | [8 empty] | 95
36090 027 | 5 | Development of the Viharagama Ratttaran watta road near Wimal Chaminda's house |  |  | 834 C Viharagama | RA | 183 | 0.5 |  | GamunuGovi So | [8 empty] | √ |  |  |  | 150
36105 028 | 6 | Development of Polkirimulla Burial ground road |  |  | 834 D Yakupitiya | RA | 215 | 0.5 |  | Sureke elder-Society | 482963.08 | [10 empty] | √ | 30
36035 029 | 7 | Concourse the upper portion of the Hingurakgoda Mr. Robert's house |  |  | 835 A Ilukpatha | RA | 215 | 0.5 |  | Suhadaelder-Society |  |  |  | √ | [8 empty] | 26
36080 030 | 8 | Concrete on the road to the Delkit Estate hospital |  |  | 835 Lathpandura East | RA | 194 | 0.5 |  | Eakamuthu elder;s So. | [8 empty] | √ |  |  |  | 170
36075 031 | 9 | Concrete on the road to the upper division of Mohomadiwatta |  |  | 835 c Maragahadeniya | RA | 200 | 0.5 |  | Samagi elder-Society | [6 empty] | √ | [5 empty] | 500
36030 032-A | 10 | Making roads in the from to kelinkanda tempal to kosgaha Handiya mechanically |  |  | 836 B -Kelinkandna | RA |  | 2 | [5 empty] | √ | [8 empty] | 90
36030 033 | 11 | Making roads in the new housing scheme mechanically |  |  | 836 F Galahitiya | RA |  | 1 | [10 empty] | √ |  |  |  | 247
36030 034 | 12 | Development of Galahitiya Main Road |  |  | 836 F Galahitiya | RA | 430 | 2 |  | Govi So. | [11 empty] | √ | 660
36045 035 | 13 | Development of Gilme Road (difficult places) |  |  | 836 palenda | RA | 200 | 0.5 |  | sanasuma elder;S So | [11 empty] | √ | 95
36045 036 | 14 | Development of Welgamgoda Road |  |  | 836 palenda | RA | 628 | 1.5 |  | sanasuma elder;S So | [11 empty] | √ | 126
36045 037 | 15 | Development of the road leading to the Muslim Village near Mosque |  |  | 836 palenda | RA | 204 | 0.5 |  | sanasuma elder;S So | [11 empty] | √ | 120
36045 038 | 16 | Development of the Paleenda veediya Bandaragama Housing Scheme |  |  | 836 palenda | RA | 310 | 1 |  | sanasuma elder;S So | 970000 | [10 empty] | √ | 77
36040 039 | 17 | Development of Mahena Batapotha watta Lime Road |  |  | 836 E palenda West | RA | 210 | 0.5 |  | MalbrriyaGarma De. So | [11 empty] | √ | 160
36040 040 | 18 | Development of Ransirigama Malbariya road |  |  | 836 E palenda West | RA | 460 | 1 |  | Garma De. So | 970000 | [10 empty] | √ | 1105
36025 041 | 19 | Development of Maguruwala road |  |  | 836 C Kapugedara | RA | 194 | 0.5 | [14 empty] | 207
36020 042 | 20 | Developmet of Walakada Main Road |  |  | 836 K Walakada | RA | 805 | 2 |  | Walakada Grma De. So. | [11 empty] | √ | 700
36010 043 | 21 | Development of old Pelpola road |  |  | 836 B Kelinkanda | RA | 180 | 0.5 |  | Widiya bandara Ga .So. | [11 empty] | √ | 145
36015 044 | 22 | Development of Lahiyagaha Kanda road |  |  | 836 I kelinkanda | RA | 185 | 0.5 |  | Grama De.So. | [7 empty] | √ |  |  |  |  | 136
36050 045 | 23 | Development of Kalewatha road near Mr.Luviiman |  |  | 836 J Bampara | RA | 200 | 0.5 |  | Kelinkanda Taruna govi JanapadaGrama De.So. | [8 empty] | √ |  |  |  | 58
36005 046 | 24 | Development of road to Ananda's house behind the military camp |  |  | 836 L Kosgulana | RA | 200 | 0.5 |  | Mahasen Govi So. | [7 empty] | √ |  |  |  |  | 102
36140 047 | 25 | Development of Athwelthota Jana Savi Mawatha around transformation (Mahawakanda) |  |  | 836 D Athwelthota | RA | 220 | 0.5 |  | Grama De.So. | 467236.77 | [10 empty] | √ | 150
36140 048 | 26 | Development of Ranji's house Road near Sudukanda Ela |  |  | 836 D Athwelthota | RA | 460 | 1 |  | Grama De.So. | [11 empty] | √ | 160
36145 049 | 27 | The causeway on the road near the Ruwan Chamara shop Diganna |  |  | 836 N Diganna | RA |  | 0.5 | [12 empty] | √
36145 050 | 28 | Development of the Mahawatta Road(to go Mr. Daya's house |  |  | 836 N Diganna | RA | 220 | 0.5 |  | Tannapita vellage De.so. | [11 empty] | √ | 38
36145 051 | 29 | Development of the road near Susantha's house |  |  | 836 N Diganna | RA | 215 | 0.5 |  | Tannapita vellage De.so. | [6 empty] | √ | [5 empty] | 78
36200 052 | 30 | Culverts for the Ketala Patta canal |  |  | 842 B Kalukandawa | RA |  | 1 |  | Tannapita vellage De.so. | [11 empty] | √ | 58
36065 053 | 31 | Development of the upper part of Rankoth road |  |  | 836 A Morapitiya | RA | 215 | 0.5 |  | Kothhena Ga.So | [11 empty] | √ | 55
36060 054 | 32 | Development of the Minikandala Amowita R oad |  |  | 836 H Morapitiya | RA | 215 | 0.5 |  | Gajaba govi Society | [11 empty] | √ | 200
36060 055 | 33 | Development of the Minikandala Nagodahena Road |  |  | 836 H Morapitiya | RA | 225 | 0.5 |  | Gajaba govi Society | 485000 | [10 empty] | √ | 33
36135 056 | 34 | Development of the Aluth mawatha Near the Mr' priyantha"s House Road |  |  | 836 G Morapitiya | RA | 215 | 0.5 |  | Grama De.So. | [11 empty] | √ | 85
36135 057 | 35 | Development of the samagi mawatha Near the Anura stores Road |  |  | 836 G Morapitiya | RA | 435 | 1 |  | Grama De.So. | [11 empty] | √ | 745
36130 058 | 36 | Development of the Madurandola pahala Road |  |  | 837 Midalana | RA | 202 | 0.5 |  | MaIthree Elder's Society | [11 empty] | √ | 67
36070 059 | 37 | Development of the Difficult area -Thiriwanagoda Road |  |  | 837 A Midalana West | RA | 175 | 0.5 |  | Samagi elder-Society | [11 empty] | √ | 510
36110 060 | 38 | Development of the galapallahena Road |  |  | 835 Lathpandura | RA | 212 | 0.5 | [9 empty] | √ |  |  |  |  | 40
36115 061 | 39 | Development of the Kanaththagoda Road |  |  | 839 B Kamburawala | RA | 220 | 0.5 |  | Suhada elder-Society | [11 empty] | √ | 660
31620 062 | 40 | Development of the Near the Pradeshiya sabha Road |  |  | 839 Baduraliya | RA | 201 | 0.5 |  | Suhada elder-Society | [8 empty] | √ |  |  |  | 250
36120 063 | 41 | Development of the Near the D S Office Road |  |  | 839 Baduraliya | RA |  | 2 |  | Suhada elder-Society | [11 empty] | √ | 1500
36125 064 | 42 | Development of the Kovilagoda Main Road |  |  | 839 C Diggoda | RA | 215 | 0.5 |  | Suhada elder-Society | 485000 | [10 empty] | √ | 210
36165 065 | 43 | Development of the Puwakgahahahena nava pitakattiya Road |  |  | 839 A Magura We. | RA | 218 | 0.5 |  | Meth Sarana elder-Society | 485000 | [10 empty] | √ | 40
36165 066 | 44 | Development of the Gurugoda Road |  |  | 839 A Magura We. | RA | 218 | 0.5 |  | Meth Sarana elder-Society | 485000 | [10 empty] | √ | 250
36160 067 | 45 | Development of the Atambagoda Road |  |  | 839 A Magura Eas. | RA | 215 | 0.5 |  | Grama De.So. | 485000 | [10 empty] | √ | 115
36175 068 | 46 | Development of the Difficult area -Dehipitiya samagi Road |  |  | 840 A Penigala | RA | 200 | 0.5 |  | Suhada elder-Society | [10 empty] | √ |  | 212
36175 069 | 47 | Development of the Pahalagoda Road |  |  | 840 A Penigala | RA | 200 | 0.5 |  | Panigala Govi. So. | [11 empty] | √ | 550
361 70070 | 48 | Development of near the Dharmarama temple Road |  |  | 840 B Addaragoda | RA |  | 0.5 |  | Dayakasabawa | [6 empty] | √
36185 071 | 49 | Development of the maduruhena Road |  |  | 841 Athale | RA | 196 | 0.5 |  | Diriya Eksath Gra So. | [6 empty] | √ | [5 empty] | 100
36155 072 | 50 | Development of the Gulanahena Road go to the mr Neel Herath House |  |  | 838 Hediglla | RA | 220 | 0.5 |  | Diyiya elder's Organi | 485000 | [10 empty] | √ | 25
36150 073 | 51 | Development of the Mellaghawela Road |  |  | 838 A Batahena | RA | 172 | 0.5 |  | Batahena Ga. So | [7 empty] | √ |  |  |  |  | 250
36190 074 | 52 | Development of the Road Near the Somarathna Stores Mellaghawela |  |  | 841 A Igurudluwa | RA | 220 | 0.5 |  | MaIthree Elder's Society | [6 empty] | √ | [5 empty] | 35
36205 075 | 53 | Devolopment of Millakadawala road |  |  | 841 B Batagodavila | RA | 218 | 0.5 |  | Suhada elder'S-Society | [7 empty] | √ |  |  |  |  | 140
36205 076 | 54 | Development of Pujalena road |  |  | 841 B Batagodavila | RA | 307 | 1 |  | Suhada elder'S-Society | [10 empty] | √ |  | 1300
36195 077 | 55 | Development of second lane by Weerasinha Kanda |  |  | 841 C Bollunna | RA | 225 | 0.5 |  | Bolunna vellage De.so. | [6 empty] | √ | [5 empty] | 177
36210 078 | 56 | Delopment of Kehel Wathuvila Road |  |  | 842-Boralugoda | RA | 195 | 0.5 |  | Boralugoda vellage De.so. | [6 empty] | √ | [5 empty] | 122
36215 079 | 57 | Development of Nilgahahena Watawala road |  |  | 842 A Thiniyawala | RA | 183 | 0.5 |  | Arunalu women so. | [11 empty] | √ | 185
| Total | [6 empty] | 39 |  |  | 5800199.85 |  |  | 5 |  |  | 6 | 6 | 7 |  | 3 | 30 | 13952
5800199.85
Note on K31: Author: